FORMER FAO AND OTHER UN STAFF ASSOCIATION

* FFOA*

FFOA/GA/2014/04							                           Page 1 of 4 pages

# Forty-fourth Session of the General Assembly

Wednesday, 28 May 2014 at 09:30 hours

Italian Conference Room, IFAD Headquarters



≈   STATEMENT OF WORK ACHIEVED DURING 2013   ≈

This document is an abstract of the full Programme Implementation Report for 2013, an internal document, to report on progress as compared with the “FFOA 2013-15 Programme of Work”.

- Ongoing Core Areas (OCA)

1.1 Institutional and External Relations Matters. The 43rd session of the FFOA General Assembly (GA) in May was well attended, and a success. The 113 participants particularly appreciated the very informative presentation by the representatives of the United Nations Joint Staff Pension Fund (UNJSPF) from the Geneva office, which looked at many aspects of the Fund.

The following additional achievements were noted:

- FFOA has started working on the organization of the next GA which will be hosted by IFAD on 28 May 2014, as well as of the Council of the Federation of Associations of Former International Civil Servants (FAFICS) to be held at FAO Headquarters from 7 to 9 July 2014;

- Representatives from the newly elected Executive Committee met with representatives from top management of the three larger UN organizations in Rome. They also met with the new UNJSPF Chief Executive Officer, and representatives of the WFP Alumni Working Group. Individual contacts were established with UGSS and AP-in-FAO;

- The list of Entities with contacts with FFOA has been updated, including the relevant contact points;

- FFOA contributed to FAO’s “Visitors’ Programme” for University students and other groups, and to the periodical Pre-Retirement Seminars organized by FAO for the retiring staff of ICCROM, IFAD, FAO, and WFP.

1.2 Pension Benefits. FFOA continued to monitor pension-related issues as they emerged during the year, primarily via the Staff Pension Committee (SPC), FAFICS, the Pension Board (PB) and the UNJSPF:

- The SPC Terms of Reference were reviewed, discussed and finally agreed with the FAO/WFP/IFAD management;

- The revision and implementation of the Mandatory Age of Separation (MAS) was followed through its review process pending final decision by the UNGA;

- Preparations for the actuarial valuation of the Fund at the end of 2013 were monitored in relation to the relevant report to the Pension Board (15-19 July) in New York. This included reviewing the demographic and economic assumptions and valuation methodology for the end of 2013;

- The application of the cost of living changes was monitored according to the relevant indices published by the UN statistical office;

- The Fund’s total investments were noted as a new record (US$ 50 billion) had been reached in November;

- The slides of the presentation, delivered at the 43th GA, were uploaded on the FFOA website where they can be consulted (www.fao.org/ffoa).

1.3 Medical Insurance. FFOA complained about the reduced activities of the JAC/MC which were now mainly limited to the preparation of a global tender for Medical and Other Insurances of active and retired staff.

Contributions for 2013 to the BMIP/MMBP plans remained unchanged for the third consecutive year.

FFOA/GA/2014/04							                             Page 2 of 4 pages

1.4 Financial Matters. In addition to maintaining the Association’s accounts and the preparation of the financial reports for the GA, the Finance Sub-Committee monitored the following items:

- The number of members in arrears with payments of annual fees has been much reduced (from 187 in January to 114 in December 2013) through the development and implementation of a monthly procedure;

- The financial reserve fund held in the Banca Popolare di Sondrio has increased from € 9,000 to € 12,000 due to some cash surplus from 2012;

- Contributions from the FAO Welfare Fund had resulted in the receipt of € 6,000. The issue will continue to be monitored in 2014. The second tranche of the contributions that had been promised, had not yet been received;

- The Emergency Fund, frozen in 2012, could not be reactivated during 2013;

- The Finance Sub-Committee initiated discussion of a detailed assessment of the FFOA financial resources in order to optimize their investment return.

1.5 Technology Support. A complete upgrade of all hardware/software installed at the FFOA offices has been possible thanks to the release of PCs and printers discarded by FAO. Six workstations have been upgraded with additional memory and new screens, and the old laser printer replaced by a less costly platform. The operating system of each PC has been migrated to Windows 7, and the database application converted to the new OS environment.

The FFOA website has been updated by a series of additional information and the creation of new sections:

- Navigation Tips have been developed to facilitate access to UNJSPF and Vanbreda sites;

- The “Recreational/Cultural Activities” page now includes reports of excursions organized by the Association, and a link to online computer training sessions;

- The “Members’ Experiences” page has been enriched by a section (“Cards from … “) dealing with information provided by members on trips, memories, special events, etc.;

- Several links have been added to the “Web Links” page;

- Additional documents have been uploaded onto the web.

The number of registered users has reached 443, with an annual increase of more than 100 units.

1.6 Publications. A revised design for the Newsbrief was initiated with adoption scheduled beginning with

No. 91, to be published in March 2014. Translation into Italian of the Newsbrief and of other documents was ensured expeditiously despite scarce resources. Volunteers are sought for translation assistance.

The following documents have been published and uploaded on the web in English and Italian:

- Newsbriefs 87, 88, 89 and 90

- The 2013 GA Provisional Report

- The “Before & After” pamphlet.

1.7 Social/Support & Recreational Activities. Many excursions and guided tours have been organized with a high level of member participation. They included:

- visits toTarquinia, Civita di Bagnoregio, Naples, Capodimonte, Tuscania, Reggia di Caserta, Vesuvio and Hercolaneum, Lake Trasimeno, Ponza, Palmarola and Zanone (a 3-day cruise), Siena, the National Park of Abruzzo and the Park of Ninfa;

- four visits to the Presidential Estate of Castelporziano;

- three guided visits to the Tiziano exhibition;

- two lunches at the Babette Restaurant.

“Coffee Mornings”. In an effort to diversify the programme, the Sub-Committee on Social Activities has introduced a new component: the “Coffee Morning”, an informal gathering of FFOA members at the FAO terrace cafeteria. The first event was organised on 8 May, the second on 12 June, the third on 10 July. From 20 September “Coffee Mornings” have taken place on a regular basis on the first Wednesday of each month.

The Year End Party was held on 18 December with an exceptionally large attendance of 74 members and guests. This is a very good sign of the interest that our Association is generating with our members.

FFOA/GA/2014/04                                                                  			                    Page 3 of 4 pages

- Project Oriented Areas (POA)

2.1 Policy and Governance

2.1.1. Review of Policy Issues. The Bureau launched some activities leading to a more efficient organization of work and procedures. A review of the policies will start in 2014.

2.1.2 Review of Statutes and Bylaws. No activity was carried out in 2013. It is planned to implement the project in 2014.

2.2 Membership

2.2.1 Membership Campaign. Two meetings of the Membership Sub-Committee took place in June and November 2013. The following proposals have already been implemented:

- A procedure to monitor payments of fees in arrear has been developed and implemented with the aim of reducing the number of member suspensions;

- A request to the UNJSPF to obtain information on elderly members (more than 80 years) who are still in receipt of a pension;

- The lists of participants at the Pre-Retirement Seminars during the last two years are in the process of being reviewed to retrieve private e-mail addresses of potential members.

In addition, the following ideas were flagged for consideration. They form the basis of the Work Plan for 2014 of    the Sub-Committee.

- FFOA to be inserted as a briefing/clearance point in the separation procedure;

- An FFOA-day to be organized once a year;

- A special meeting of the Executive Committee dedicated to promote membership and to improve interaction among active and retired staff should be organized with staff associations;

- The Finance Sub-Committee to develop and present a case in collaboration with the Membership Sub-Committee, whether or not there is a justification for an increase in the membership fees;

- Alternative ways of financing the FFOA operations should also be explored:

  - by looking into the possibility of increasing the number of associate members,

  - by increasing the total contribution for new life members, and

  - by launching a campaign for voluntary contributions.

2.2.2 Membership Data. The updating procedures for the FFOA Database have been improved by running several data cross-reference verification procedures.

2.3 Communications and Training

2.3.1 Communication Tools. Despite the elaboration of some ideas on how to promote a more interactive version of the Newsbrief and of the Website, 2013 did not allow much time for the actual development of these areas.

As had already been mentioned before, a first version of the revised design of the Newsbrief should be released in March 2014, while its complete redesign (to make it more interactive), should be ready by the end of 2014. The refurbishing of the current version of the Website has been postponed to 2015.

The planned development of videos has not been possible due to lack of resources.

2.3.2 Training and Workshops. A Workshop on the Internet was delivered to members of the Executive Committee in April. The same Workshop was then held for FFOA members in November. Documentation used during the presentations was distributed to all members. Immediately after the Workshop members were informed that a special link was available from the Recreational/Cultural page of the FFOA website to access free online courses over the Internet (covering Word, Excel, PowerPoint, etc.).

2.4 Programme Development and Follow-up

2.4.1 Programme Development. The Programme Sub-Committee finalized the Programme of Work in early 2013 resulting in the Work Plan for 2013, approved by the Executive Committee on 6 March.

FFOA/GA/2014/04                                                                  			       Page 4 of 4 pages

2.4.2 Programme Reporting. A first version of a standard template for progress reporting was used in June. The second Progress Report (in November) used a different layout, which was more favorably received by the Executive Committee.

The FFOA presented an abstract of its 2013-2015 Programme of Work to the May 2013 GA and for the May 2014 GA it provides the present Statement of Work achieved during 2013, i.e. the present report.

2.4.3 Programme Updates. The 2013-15 Programme of Work will be reviewed in early 2014 based on the work accomplished in 2013, and possibly including additional project ideas for 2014.

3. FFOA Statistics

| Membership |  |  | (Source: FFOA Database as at 31.12.2013) |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| As at | Total | In Italy |  |  |  |  |  |  |  |  |
| 01.09.2002 | 2389 | 1510 |  |  |  |  |  |  |  |  |
| 01.09.2003 | 2338 | 1489 |  |  |  |  |  |  |  |  |
| 01.09.2004 | 2433 | 1576 |  |  |  |  |  |  |  |  |
| 01.09.2005 | 2317 | 1498 |  |  |  |  |  |  |  |  |
| 01.03.2006 | 2254 | 1446 |  |  |  |  |  |  |  |  |
| 01.03.2007 | 2276 | 1459 |  |  |  |  |  |  |  |  |
| 01.03.2008 | 2315 | 1492 |  |  |  |  |  |  |  |  |
| 01.03.2009 | 2259 | 1436 |  |  |  |  |  |  |  |  |
| 01.03.2010 | 2163 | 1387 |  |  |  |  |  |  |  |  |
| 31.12.2010 | 2048 | 1315 |  |  |  |  |  |  |  |  |
| 31.12.2011 | 2075 | 1358 |  |  |  |  |  |  |  |  |
| 31.12.2012 | 2172 | 1463 |  |  |  |  |  |  |  |  |
| 31.12.2013 | 2182 | 1491 |  |  |  |  |  |  |  |  |
|  |  |  |  | of which in 2013: 120 new members |  | 65 from FAO |  |  |  |  |
|  |  |  |  |  |  | 11 from IFAD |  |  |  |  |
|  |  |  |  |  |  | 17 from WFP |  |  |  |  |
|  |  |  |  |  |  | 27 from other Org.s |  |  |  |  |

40  suspended

70  deceased

| Members with and without e-mail by age and location |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| E-mail / No E-mail |  |  |  |  | E-mail / No E-mail |  |  |  |
| by Age |  |  |  |  | by Location |  |  |  |
| By age | Total | of which |  |  | By Loc. | Total | of which |  |
|  |  | e-mail | no e-mail |  |  |  | e-mail | no e-mail |
| Total | 2182 | 1382 | 800 |  | Total | 2182 | 1382 | 800 |
| No DOB | 338 | 46 | 292 |  |  |  |  |  |
| Less 61 | 78 | 75 | 3 |  | Italy | 1491 | 994 | 497 |
| 61-65 | 218 | 208 | 10 |  | Europe | 404 | 228 | 176 |
| 66-70 | 358 | 316 | 42 |  | N+S Am | 135 | 78 | 57 |
| 71-75 | 430 | 330 | 100 |  | Africa | 50 | 28 | 22 |
| 76-80 | 324 | 193 | 131 |  | Far East | 62 | 30 | 32 |
| 81-85 | 203 | 105 | 98 |  | Near East | 17 | 10 | 7 |
| 86 + over | 233 | 109 | 124 |  | Australia | 23 | 14 | 9 |

No. of website users: 443

No. of supported “Visitor Programme” sessions: 25

This is our report on our activities for the past year, for which we hope you will give your approval (draft resolution FFOA/GA/2014/06/B refers).