Timeline for the FFF Call for Proposals 2015

| Action | Time (deadline) | Responsible |
| --- | --- | --- |
| Preparation of the call for proposals for Nakuru and Laikipia | Thursday, 28 May | Kisoyan |
| Organization of the selection committee at county level* | Friday,5 June | Oscar |
| Issue the call for proposals at county level in the 2 counties | Friday, 29 May | Geoffrey & FF- SPAK CD programme officer |
| Deadline for submission of proposals. Total 4 weeks for proposals preparation | Friday, 26 June | Geoffrey & FF- SPAK CD programme officer |
| Selection process: (FF-SPAK pre-screening and prepare a table according selection criteria; send the proposals to the committee, selection committee review and select proposals. Total 1 week | Friday, 3 July | Geoffrey & FF- SPAK CD programme officer |
| Communication to selected PO | Friday, 3 July | Kisoyan (with county government) |
| Meetings with selected PO to discuss and review proposals to put them ready for LoA. In these meetings will participate the core team and Jhony Zapata | Week of 6 – 10 July | Geoffrey & FF- SPAK CD programme officer |
| MoU or similar arrangement between selected POs and FF-SPAK. Total 1 week | Week 13 – 17 July | Geoffrey & FF- SPAK CD programme officer |
| Preparation of the 6 to 8 Letter of Agreements (LoA) with the selected POs (3 to 4 by county). Total 3 weeks | 13 – 31 July | Jhony + Kisoyan |
| Ceremony at county level of signature and first payments | Week of 3 – 7 August | Oscar |

* Members of the selection committee at county level:

- FF-SPAK

- KFS focal point for the FFF

- FFF Facilitator

- We Effect officer rural development

- County government focal point for the FFF