**Team meeting: 17 November 2020**

**Participants:** PB, SS, FG, GR, MFL, JZ, SG, KV, SA,

**Chair**: DM

**Note taker:** NS

**Agenda:**

|  |  |  |
| --- | --- | --- |
| **Team report** | **DESCRIPTION**  **(summary if discussion – main points only)** | **ACTION**  **(to be checked at next meeting)** |
| New manager/David Kaimowitz | The contract will start 15 December. David will be participating the Retreat (but not the preparation) and strategic issues prior to contract. FFF Team hopes that David could also join the FMM meeting 25 November and FCDO meeting | Marguerite/Jhony will ask David if he could present the FMM slides |
| Introduction of Samuel Adeyanju | Samuel has joined FFF and the communication and outreach team as an intern, working 1 day per week. Until the corona situation improves, the work will be conducted as distance work. Samuel will work with reports, communication strategy and other tasks |  |
| Updates on donor situation (GIZ, BMZ, FCDO,) | **GIZ –** Zoraya and Svea working on the budgets. The MUL product and budget have been sent to GIZ.  **BMZ** - Procedures for the preparation of the agreement are on-going..  **FCDO** – No further news, but FFF should start developing the workplan for the first year. | GIZ – Svea to waiting for feedback, hopefully already this week  BMZ – List of countries has to be sent to BMZ due to differences in country sanction policies.  FCDO - Sophie finds out a date for the FCDO meeting with David |
| Retreat | Facilitators should complete the PP templates this week, but the current format lacks highlights for communication/outreaching purposes  Francesca is the focal point/coordinator for the Retreat | Marguerite will contact facilitators this week in order to identify success stories and other communication material for outreach purposes  Sophie and Jhony will propose chairs for each session    Francesca will share more defined program this week  Duncan supports updating reporting templates |
| Resilience Case Studies | Duncan has finalized the edits of new cases  AgriCord has finilised the draft texts for the publication. David’s contribution is needed for the foreword, but can be acquired in December.  AgriCord has launched the Building Resilience Toolkit part I- *FO members assessing climate risks and designing adaptation.* The ToTs are also running starting from this week | Duncan will share the edited cases with Marguerite  Noora will share the publication (draft text) for comments  Noora will share the link and password for the Tool |
| Legal and Sustainable Wood Coalition | The participation of FFF would have some practical indications, such as providing success stories, participating in surveys etc.  Duncan suggested that FFF could provide a position paper to in line with the objectives of the coalition  Noora called for high profile of inclusion of and support for smallholders in traceable wood-value chains  The team was willing to join the coalition. The core group dealing with the initiative is Duncan, Pauline, Sophie and Jhony | Jhony will arrange a meeting with Thais Linhares/Team Leader Forest Governance and Economics |
| Other issues | Rachel Butler/ Executive Director of Global Timber Forum has contacted Duncan regarding promotion of timber and trade associations | Duncan will share the briefing/e-mail from GTF |
| **Next Chair: Note Taker:** | * Senesie * Bolin |  |

|  |  |
| --- | --- |
| **NEXT CHAIR**  Bolin  Buffle  DeRobert  Grouwels  Guarascio  MacQueen  Senesie  Simola  Zapata | **NEXT NOTE TAKER**  Bolin  Buffle  DeRobert  Grouwels  Guarascio  MacQueen  Senesie  Simola  Zapata |

**Sari Seppanen**

Coordination Specialist: UNDAF/SDG Partnership Platform

ASNETin toimintaan: [https://agrifoodkenya.com/asnet-up-to-transform-agriculture-sector-in-kenya/](https://eur02.safelinks.protection.outlook.com/?url=https%3A%2F%2Fagrifoodkenya.com%2Fasnet-up-to-transform-agriculture-sector-in-kenya%2F&data=04%7C01%7C%7C811a8d78a76f42deb52a08d887049821%7Cc10c53fbad1e4893a1acee30fbe7b31c%7C0%7C1%7C637407801218639817%7CUnknown%7CTWFpbGZsb3d8eyJWIjoiMC4wLjAwMDAiLCJQIjoiV2luMzIiLCJBTiI6Ik1haWwiLCJXVCI6Mn0%3D%7C3000&sdata=qE73SO1ufE4LUeSo6kXT0jnrZEc%2F2rHAXTXGD%2FbpPmo%3D&reserved=0)

SDG PARTNERSHIP PLATFORM KENYA

PROGRAM DOCUMENT

SDG2 FOOD AND NUTRITION SECURITY WINDOW

UN flagship program

The program builds on the experiences and success to date of the SDG Partnership Platform in Kenya to accelerate engagement and implementation of the UN Multi-Partner Trust Fund (MPTF) that is currently under design as part of enhancing the effective use of the United Nations Development Coordination Framework (UNDCF 2018-2022) structures and delivering on the UN Reforms in Kenya.

The Overall goal of the SDG Window 2 on food and nutrition security window is to improve the enabling environment and increased investments for the agriculture sector in Kenya

This will be achieved through the following outcomes:

1. i. Increased **SDG-compliant investment** in nutrition-sensitive, climate proofed agriculture of USD 100 million in the next five years
2. ii. Increased **income and employment**, especially for women and youth, in the nutrition-sensitive agriculture sector and food system for 50,000 Kenyans (50% women; 30% youth)
3. iii. Increased access for 100,000 local consumers to **safe and nutritious foods**
4. iv. Strengthened **policies, systems and structures at national and county levels** to help catalyze investments in the delivery of the Agriculture Sector Growth and Transformation Strategy (ASGTS), Kenya Food and Nutrition Security Policy, it’s Implementation Framework (FNSP-IF), and Kenya National Nutrition Action Plan.